## Introduction to this template
Template for budgeting for ICT systems acquisition
This ICT systems acquisition budget template will help you develop a budget for the complete process of acquiring a new technology-based system.
This template is not is a primer for systems acquisition or on budgeting in general. But it will prompt you for the things you need to consider when working out what it will cost to acquire a new technology system.
It is really easy to underestimate the effort and costs involved when preparing your budget. The ICT systems acquisition budget template has been developed to help you think about all the activities and costs you may need to consider. The template has been designed to provide a clear way of presenting the processes, what needs to be purchased, what support is required and for calculating the costs. What you’ll need to include will vary depending on the nature of the system - for example whether it is for service delivery, financial, email and so on.
The template should be read in conjunction with our resource “How to choose a software package for delivering services to clients”

## Guidelines for this template
Spreadsheet user guidelines
All totals are calculated using the "subtotal" calculation =subtotal(9,nn:nn) where nn:nn is the cell range to sum. | It’s a lovely calculation as it ignores any other cell within the range nn:nn that also has a "=subtotal(9,mm:mm)" calculation. This means you don’t have to worry about adding individual cells to get sub totals and grand totals. BUT - it cannot be mixed with the more common =sum(nn:nn) calulation without mucking up all the calculations. So tamper with them with care :)
All fields shaded mild yellow are data entry fields, or calls to named cells.
The "clear" cells/fields are used either for entry of descriptions or for calculations. In the case of the calculations, take care not to overwrite them
The values such as user numbers, costs of resources, unit travel costs etc are setup as named cells in the "assumptions & unit cost" worksheet. | This makes it easy to globally change values such as user numbers and exchange rates rather than in a number of places in the spreadsheet

## Assumptions & unit costs
Yellow cells - for direct entry of numerical values or calls to named cells
Clear cells - where values are calculated or descriptions entered
Description | Unit cost
ICT consultant (hourly) | 150 | ** or whatever external resource types you are using, "named" so they can be easily pulled into the budget worksheets in multiple places
Business Analyst (hourly) | 85
Nightly expenses (accom & evening meal) | 200
Average return airfare inc taxis (to-from airports) | 550 | (1 wk notice, worst case)
Average vehicle expenses ($0.62/km @ 300km) | 190
Car rental per day | 100
Catering - cost per participant/day | 35
Venue hire | 1000
User numbers
Total users (CMS) - client management system | 15
Total users (email) | 20
Contingency & exchange rates
Contingency % | 15%
Australian exchange rate | 0.8
US exchange rate | 0.85
Assumptions
Requirements gathering | opex | Operational/expenses
System selection | capex | Capital
System implementation | capex | Capital
Post implementation review (PIR) | opex | Operational/expenses

## Budget ddmmmyy
Yellow cells - for direct entry of numerical values or calls to named cells
Clear cells - where values are calculated or descriptions entered
| Capex |  |  | Opex |  |  | Tot capex & opex | Ongoing annual expense |  |  | Ongoing annual capital
Description | Qty | Unit cost | Tot cost | Qty | Unit cost | Tot cost |  | Qty | Unit cost | Tot cost | Qty | Unit cost | Tot cost | Comments
Requirements budget
Project management, BA & staffing
ICT consultant |  |  | 0 |  | 150 | 0 | 0 |  |  | 0 |  |  | 0
Business Analyst (BA) |  |  | 0 |  | 85 | 0 | 0 |  |  | 0 |  |  | 0
Backfilling staff |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
?? |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
Total project mgt, BA & staffing |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
Travel
Travel - 1 day trips |  |  | 0 |  | 550 | 0 | 0 |  |  | 0 |  |  | 0
Travel - 2 day trips |  |  | 0 |  | 750 | 0 | 0 |  |  | 0 |  |  | 0
Venue hire |  |  | 0 |  | 1000 | 0 | 0 |  |  | 0 |  |  | 0
?? |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
Total travel |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
Sundry
Lawyers fees for tender/RFP |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
?? |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
Incidentals |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
Total sundry |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
Subtotal ex contingency |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
General contingency |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
Total requirements budget |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
Selection budget
Project management, BA & staffing
ICT consultant |  | 150 | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
Business Analyst (BA) |  | 85 | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
Backfilling staff |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
?? |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
Total project mgt, BA & staffing |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
Travel
Travel - 1 day trips |  | 550 | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
Travel - 2 day trips |  | 750 | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
Venue hire |  | 1000 | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
?? |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
Total travel |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
Sundry
Lawyers fees for supplier contracts |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
?? |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
Incidentals |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
Total sundry |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
Subtotal ex contingency |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
General contingency |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
Total selection budget |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
Implementation budget
Project management, BA & staffing
ICT consultant |  | 150 | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
Business Analyst (BA) |  | 85 | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
Backfilling staff |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
?? |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
Total project mgt, BA & staffing |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
Software, hardware & supplier costs
Number full concurrent licences | 11 | [12 empty] | The user numbers can be in this worksheet or as named cells in the "assumptions & unit cost" worksheet. But if in the latter, then this will change values in all worksheets, which you may not want if you different versions of the budget worksheets over the life of the project
Number limited concurrent licences | 15
<name of the package> software |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
<supplier name> implementation (inc. configuration, reports, supplier provided training, additional development costs, etc) |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | These costs could be itemised separately
Hardware (servers, discs, etc) |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
Server licenses (SQL, Windows, etc) |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
Installation of hardware & software |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
User devices (PCs, laptops & tablets) |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | Include the hardare & software costs. If these are to be leased, the costs will be in the "Annual expense" rather than "Capex" columns, though there may be some setup costs that are captialised
Annual hosting fees |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | For cloud based and/or hosted systems & services
Annual software maintenance fees |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | To cover ongoing upgrades to the software
Annual support fees |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | For support from the supplier - this may be a fixed fee or your estimate of the ad hoc costs you'd expect to pay each year
Integration with other systems (financial, email,etc) |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
Additional development work each year |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | Ongoing development costs of package or additional modules, etc
Total software, hardware & supplier costs |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
Implementation costs (ex supplier costs)
Travel - PM, BA & trainers - 1 day trips |  | 550 | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
Travel - PM, BA & trainers - 2 day trips |  | 750 | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
Venue hire |  | 1000 | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
?? |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
Total implementation (ex supplier) costs |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
Sundry
Lawyers fees for final contract |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
?? |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
Incidentals |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
Total sundry |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
Subtotal ex contingency |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
General contingency |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
Total implementation budget |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
Grand total system acquisition |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0
Note on H3: Infoxchange: This is the only place/column in this template using a "=nn+nn" style calulation rather than "=subtotal(9,nn:nn)